## Backlog
ID | Epic | Feature | User Story | Phase | Priority | Complexity | Effort (pts) | Dependencies | Source Doc
TB-001 | Listing Lifecycle | Unified status glossary | As an agency owner, I see one clear reason and one correct fix action for any non-active listing (Not Posted / Insufficient Credits / Ad License Expired / Deleted) | MVP | P0 | M | 8 | Listings, Credits, License | 30_TUBA_NEXT_GENERATION_SPEC.md #1
TB-002 | Listing Lifecycle | Computed listing status | As a system, listing status is derived from license validity + credit balance + user action, not manually set | MVP | P0 | M | 8 | License, Credits | 30_TUBA_NEXT_GENERATION_SPEC.md #1
TB-003 | Listing Lifecycle | Bulk republish / bulk tier change | As a listing manager, I can select multiple listings and republish or change tier in one action | V3 | P2 | M | 5 | TB-001 | 26_UX_PATTERN_LIBRARY.md
TB-004 | Licensing | License → dependent listings link | As an agency owner, I see every listing tied to a license from the license's own detail page | MVP | P0 | S | 5 | License, Listing | 30_TUBA_NEXT_GENERATION_SPEC.md #6
TB-005 | Licensing | Expiry countdown + forecast notification | As an agency owner, I get warned 14/7/1 days before a license lapses, with the affected listings named | MVP | P0 | M | 5 | TB-004, Notifications pipeline | 34_AI_ARCHITECTURE.md
TB-006 | Licensing | Multi-license per agency | As a multi-branch agency, I can attach different licenses to different listings/branches | V3 | P2 | L | 13 | TB-004 | 30_TUBA_NEXT_GENERATION_SPEC.md #6
TB-007 | Credits & Packages | Opt-in auto-spend with full log | As an agency owner, Smart-Credit-Utilization-equivalent auto-spend is off by default and every auto-spend event is logged distinctly from manual spend | MVP | P0 | S | 5 | Credit ledger | 30_TUBA_NEXT_GENERATION_SPEC.md #2
TB-008 | Credits & Packages | Credit ROI panel | As an agency owner, I see leads generated per credit spent, not just a balance | V2 | P1 | M | 8 | Credits, Leads, Reports | 30_TUBA_NEXT_GENERATION_SPEC.md #2
TB-009 | Credits & Packages | Package tier recommendation | As an agency owner, I get a recommended tier based on my actual usage pattern | V2 | P1 | M | 8 | TB-008 | 30_TUBA_NEXT_GENERATION_SPEC.md #2
TB-010 | Leads / CRM | SLA age indicator on lead rows | As an agent, I see how long a lead has gone without follow-up, visually escalating | MVP | P0 | S | 5 | Leads table | 30_TUBA_NEXT_GENERATION_SPEC.md #3
TB-011 | Leads / CRM | Unnamed-lead auto-enrichment | As an agent, leads captured without a name get auto-enriched from caller/WhatsApp profile where available | V2 | P1 | M | 8 | Leads, channel integrations | 34_AI_ARCHITECTURE.md
TB-012 | Leads / CRM | Pipeline board view | As an agent, I can view/drag leads through New/Contacted/Qualified/Viewing/Offer/Closed stages | V2 | P1 | L | 13 | TB-010 | 30_TUBA_NEXT_GENERATION_SPEC.md #3
TB-013 | Leads / CRM | Rules-based lead scoring | As an agent, each lead shows a score based on channel, listing price/type, response history | V2 | P1 | M | 8 | Leads, Listings history | 34_AI_ARCHITECTURE.md
TB-014 | Leads / CRM | Duplicate-lead detection | As an agent, leads from the same contact across channels are merged or flagged | V3 | P2 | M | 8 | TB-013 | 30_TUBA_NEXT_GENERATION_SPEC.md #3
TB-015 | Leads / CRM | Auto-assignment rules | As an agency owner, new leads round-robin or route to a listing's owning agent automatically | V2 | P1 | M | 8 | Leads, Staff roles | 30_TUBA_NEXT_GENERATION_SPEC.md #3
TB-016 | Gamification | Disclose badge thresholds | As an agent, every Locked badge shows its exact threshold and my current distance from it | MVP | P0 | S | 3 | Agent Performance scoring | 30_TUBA_NEXT_GENERATION_SPEC.md #4
TB-017 | Gamification | AI badge-coaching copy | As an agent, I get a specific, generated suggestion for the fastest way to close my nearest badge gap | Quick Win | P0 | S | 5 | TB-016, LLM integration | 34_AI_ARCHITECTURE.md
TB-018 | Gamification | Branch-scoped leaderboards | As a multi-branch agency owner, I can view leaderboards per branch, not just agency-wide | V3 | P2 | M | 8 | TB-006, Staff roles | 30_TUBA_NEXT_GENERATION_SPEC.md #4
TB-019 | Reporting | KPI cards with explicit baseline | As an agency owner, every percentage delta states what period it's compared against | Quick Win | P0 | S | 3 | Dashboard, Reports | 30_TUBA_NEXT_GENERATION_SPEC.md #5
TB-020 | Reporting | Report builder + saved configs | As an agency owner, I can build and save a report definition (segment + date range + metrics) | V2 | P1 | L | 13 | Reporting service | 30_TUBA_NEXT_GENERATION_SPEC.md #5
TB-021 | Reporting | CSV/PDF export | As an agency owner, I can export any report view | MVP | P0 | S | 5 | Reports | 10_REPORTING_REVIEW.md
TB-022 | Reporting | Scheduled report delivery | As an agency owner, I receive a report digest by email/Slack on a schedule | V2 | P1 | M | 8 | TB-020, Notification pipeline | 30_TUBA_NEXT_GENERATION_SPEC.md #5
TB-023 | Reporting | Natural-language report query | As an agency owner, I can ask 'which listings underperformed this month' in plain language | V3 | P3 | L | 13 | TB-020, LLM integration | 34_AI_ARCHITECTURE.md
TB-024 | Permissions | Six-role RBAC model | As an agency owner, I assign Admin/Listing Manager/Agent/Finance/Read-only Analyst roles at invite time | V2 | P1 | L | 13 | Staff/User model | 27_PERMISSION_MATRIX.md
TB-025 | Permissions | Audit log | As an agency owner, I see who changed what and when across licenses, credits, and staff | V2 | P1 | M | 8 | TB-024 | 27_PERMISSION_MATRIX.md
TB-026 | Permissions | Scoped license visibility | As an agency owner, I grant license visibility per-role, not agency-wide only | V2 | P1 | S | 5 | TB-024, TB-004 | 27_PERMISSION_MATRIX.md
TB-027 | Notifications | Split transactional vs marketing streams | As a user, I can filter notifications to just actionable/transactional items | MVP | P0 | S | 5 | Notification pipeline | 30_TUBA_NEXT_GENERATION_SPEC.md #8
TB-028 | Notifications | Generic event-driven notification pipeline | As a platform, any domain event (lead.created, license.expiring, badge.near_unlock) can publish a notification without bespoke per-feature code | MVP | P0 | M | 8 | Pub/sub infra | 30_TUBA_NEXT_GENERATION_SPEC.md #8
TB-029 | Settings | Extend AI generation to agency description | As an agency owner, I can AI-generate my agency description bilingually, matching the existing agent-bio pattern | Quick Win | P2 | S | 3 | LLM integration | 30_TUBA_NEXT_GENERATION_SPEC.md #9
TB-030 | Settings | Consent toggles default off | As a user, marketing/data-usage consent toggles are off by default, not on | Quick Win | P0 | S | 1 | Preferences | 30_TUBA_NEXT_GENERATION_SPEC.md #9
TB-031 | AI / Listing Quality | Publish-time quality score | As a listing manager, I see a completeness/quality score before publishing, not only post-hoc via gamification | MVP | P0 | M | 8 | Listing, Media | 34_AI_ARCHITECTURE.md
TB-032 | AI / Listing Quality | Draft-recovery credit calculator | As a listing manager, a Draft blocked on Insufficient Credits shows exactly how many more credits are needed | Quick Win | P1 | S | 3 | Credits, Draft status | 34_AI_ARCHITECTURE.md
TB-033 | AI / Listing Quality | Bilingual description generation | As a listing manager, I can AI-generate a property description in English and Arabic | V2 | P1 | M | 8 | Listing, LLM integration | 34_AI_ARCHITECTURE.md
TB-034 | AI / Listing Quality | Image quality analysis | As a listing manager, uploaded photos are scored for blur/coverage/watermark and feed the quality score | V2 | P1 | M | 8 | Media, TB-031 | 34_AI_ARCHITECTURE.md
TB-035 | AI / Listing Quality | Duplicate listing detection | As an agency owner, near-duplicate listings within my inventory are flagged | V3 | P2 | M | 8 | Listing | 34_AI_ARCHITECTURE.md
TB-036 | AI / Market | Pricing suggestions | As a listing manager, I get a suggested price range based on comparable listings | V3 | P2 | L | 13 | Market comp data (external) | 34_AI_ARCHITECTURE.md
TB-037 | Search | Global search across listings/leads/staff | As any user, I can search once and see matches across every module | V2 | P1 | M | 8 | Search index | 26_UX_PATTERN_LIBRARY.md
TB-038 | Search | Saved filters / saved views | As a power user, I can save a filter combination and return to it later | V2 | P1 | S | 5 | Listings/Leads filter state | 26_UX_PATTERN_LIBRARY.md
TB-039 | Platform | Event-sourced credit ledger | As a platform, Credit Transactions are an immutable append-only log, balance is derived | MVP | P0 | M | 8 | Credits data model | 30_TUBA_NEXT_GENERATION_SPEC.md #2
TB-040 | Platform | Decouple bot-defense from token refresh hot path | As a platform, session refresh does not block on a synchronous challenge round-trip on every page load | MVP | P0 | M | 5 | Auth service | 33_PERFORMANCE_ARCHITECTURE.md

## Summary by Phase
Phase | Item Count | Total Effort (pts)
Quick Win | 5 | 15
MVP | 13 | 78
V2 | 15 | 129
V3 | 7 | 68